## Sheet1
TASK / PROCESS | Contact Person | RESPONSIBILITY OF | CURRENT STATUS | REMARKS
FACILITY NEEDS
SD CARD for camera -@ GHS1,350 for 512GB | Mr. George | Dr. Patricia / Angela | Complete
MINI PAC software for Ultrasound - @ GHS7,600 | Mr. Kwame Asante | Dr. Essel /Angela | Pending
Office Locker for Office Manager | Angela | Angela | Pending
Telemedicine in exam rooms | Wise Infotech | Drs Sedo / Essel / Angela | Complete
Intercom Telecel - @GHS19,540.00 | Telecel -Senyo | Angela | Pending
Blotchy paint on some walls | Mr.. Lawson | Angela | Pending
Bollards for the parking space | Mr. Lawson | Dr Essel / Angela | Pending
Demarcation of the parking spaces | Mr. Lawson | Dr Essel / Angela | Pending
Signage at the Front | Frank Siamah | Drs Sedo / Essel / Angela | Pending
Fumigation - @ GHS2,500 (every quarter or 6 months) | LaDMA | Angela | Pending
Bannisters | Mr Lawson | Cobba | Complete
Door Flaps | Mr Lawson | Sedo | Complete
Billboard | Frank | Angela, Sedo, Cobba | pending | No change
Security Post | Angela | Dr Patricia | pending
Stair protector | Angela | Dr Patricia | pending
Reception paintings | Mr lawson/Metrova | Sedo/Martina | pending | notified parties. Be done 5/11/2025
mission/vision | Frank | Angela, Sedo | Complete
Privacy Curtains for Sick Bay & Ultrasound room | Angela | Angela | Pending - currently using privacy screens for sick bay
Exam room dispensers/paintings | Mr Lawson/Metrova | Sedo/Martina | Dispensers complete
Letter to Landloard - repairs | Mr Zu/Cobba | Sedo | Meet Alex 5/4/2025 | Rain gutter restored
Leak | Mr Lawson | Angela | Complete
Pharmacy-AC,Blinds,high chairs | Mr Lawson/Metrova/Angela | Dr Patricia | Partially complete | Metrova notified
Safe | Angela | Cobba | Complete
Cabinetry in Ultrasound/Echo Room | Metrova/Carpenter | Sedo/Angela | Pending | Metrova notified
Clinic e=Extension Drawings | Michael | Sedo/ Angela | Complete | Michael notified by Sedo
Business Cards | Frank Siamah | Dr. Tamakloe / Angela | Pending
Generator Lease extension | Mr. Lawson | Drs Sedo / Essel Sarah | pending
NEGOTIATIONS/PARTNERSHIPS
Bank Hospital | Grace Awotwe/Anne Rita | Sedo/cobba | Complete | Completed
Accra Medical Centre |  | Dr. Essel | Complete
Pink Clinic wtith Metro TV / Ignite Media | Adriana _Metro TV | Dr. Patricia / Angela | Complete | Completed
Global Entrepreneurship Festival - GEF |  | Angela /Charles | Complete
PHARMACY
Supplies/shelve signage | Frank/Metrova | Angela/Dr Patricia | Partially complete | Frank Siamah assessed shelves
STAFF ORIENTATION
Soft Skills Training | Rami | Angela/Cobba | In progress | First 2 sessions completed
ACLS Training for clinical staff - @GHS1,200 per head | Mr. George | Dr. Patricia / Angela | Complete | i) BLS - 900 cedis (ii) ACLS - 1,100 cedis (iii) BLS - 800 cedis (iv) ACLS - 1,200 cedis
Fire Safety Training for all staff | Fire Service Contact | Angela | Pending
STAFF ORIENTATION
MARKETING
Monthly Newsletter | Charles | Charles |  | Posted
Podcast with Dr. Gbedemah | Charles | Charles / Dr. Gbedemah | Pending
Physician profiles on company website | Charles |  | Pending
Marketing for potential corporate clients
INFORMATION TECHNOLOGY
website | Kwesi | Sedo | Working progress | Working Physician profile pictures
Teams | Kwesi/Dereck | Angela/Sedo | pending
EMR - Medsys | Nokio | Sedo /Angela | pending | Dry run with vendor
Telemedicine | Wise Infotech | Cobba/Sedo | complete | Exam room 1 set up for telemedicine
Telephones - for intercom | Kwesi/Dereck | Angela/Sedo | Working progress
Premedgo | Jessica Boateng | Angela | In progress
REGISTRATIONS
Hefra |  | Angela/dr Patricia | Complete
EPA |  | Angela/dr Patricia | Complete | received forms & bill of GHS3,315.00
NHIA |  | Angela/dr Patricia | Complete
GHS - District |  | Angela/dr Patricia | Pending
Physician's MDC certification | Cobba's contact person | Wendy | In progress | Almost complete
Application for privileges TBH | Dr Charlotte Osafo TBH | Wendy | Complete
Business Operating Permit -@GHS2,000 | LaDMA | Angela | Pending | Pending
FACILITY WORKS - NEWLAND INTERIORS
Artwork re-print - 1piece (@ GHS200) | Metrova | Angela | GH¢243.80 (+ VAT) | Pending
Footrests - pharmacy - (3@ GHS900 each) | Metrova | Angela | GH¢3291.30 (+VAT) | Pending
Adjustment of desk leg - pharmacy | Metrova | Angela | GH¢316.94 (+ VAT) | Pending
Cover for pharmacy pipes with push open door | Metrova | Angela | GH¢1,283.61 (+ VAT) | Pending
Gas lifts for pharmacy cabinets(8 @GHS78 each) | Metrova | Angela | GH¢760.66 (+ VAT) | Pending
Vinyl bolster (1 @ GHS700 ) | Metrova | Angela | GH¢853.30 (+ VAT) | Pending
Vinyl Seat Cushion (1 @ GHS1,000) | Metrova | Angela | GH¢1,219.00 (+ VAT) | Pending
Cladding for pharmacy seating area (@GHS7,189) | Metrova | Angela | GH¢8,763.39 (+ VAT) | Pending
Reception Blinds (@ GHS11,470) | Metrova | Angela | GH¢13,981.93 (+ VAT) | Pending
Pharmacy Blind (@GHS6,241) | Metrova | Angela | GH¢7,607.78 (+ VAT) | Pending
Workmanship for Blinds (@GHS800.00) | Metrova | Angela | GH¢975.20 (+ VAT) | Pending
Sickbay Cabinets & Worktop (@ GHS15,938.00) | Metrova | Angela | GH¢19,428.42 (+ VAT) | Pending
Sickbay sink and tap (@ GHS1,950.00) | Metrova | Angela | GH¢2,377.05 (+ VAT) | Pending
NHIS OUTSTANDING TASKS
The Organogram | Mad. Anita Arthur | Angela | Complete
Book for documentation on all referrals to other facilities | Angela | Angela | Complete | Pending
Incident Report Book | Angela | Angela | Complete | Pending
Access to ambulance (Contacts must be displayed) | Angela | Angela | Pending | Pending
Fire Extinguisher-expiry must be visibly displayed on it | Fire Service Team | Angela | Pending | Pending
Nursing and Lab protocols must be displayed | Wendy /William | Angela |  | Pending
Implement Staff Surveys regarding working conditions | Angela | Angela | Pending | Pending
Training Plan | Angela | Angela | Pending | Pending